## ProjectTracker
PROJECT SHIELD (Monday-Thursday) - As of 3-10-2020
CATEGORY | TASK | OWNER | PRIORITY | DUE DATE | START | END | % COMPLETE | DONE | COMMENTS
Continuous / Ongoing
Regulatory /Committee Daily Updates |  |  | HIGH |  |  |  | 100% | 1
Board updates |  |  | HIGH |  |  |  |  | 0
Regulatory |  |  | LOW |  |  |  |  | 0
|  |  | HIGH |  |  |  |  | 0
|  |  | MEDIUM |  |  |  |  | 0
|  |  | LOW |  |  |  |  | 0
Deloitte (Meeting Wed, 11-March)
|  |  |  | 2020-03-08 |  |  | 100% | 0
0
|  |  |  | 2020-03-10 |  |  |  | 0
|  |  |  | 2020-03-08 |  |  | 100% | 1
|  |  |  | 2020-03-10 |  |  |  | 0
|  |  |  | 2020-03-08 |  |  | 100% | 1
|  |  |  | TBD |  |  |  | 0
|  |  |  | 2020-03-08 |  |  | 100% | 1
|  |  |  | 2020-03-08 |  |  | 100% | 1
|  |  |  | 2020-03-08 |  |  | 100% | 1
|  |  |  | 2020-03-08 |  |  | 100% | 1
|  |  |  | 2020-03-08 |  |  | 100% | 1
|  |  |  | 2020-03-10 |  |  |  | 0
|  |  |  | 2020-03-10 |  |  |  | 0
HR Management / Facilities
Contract Boeker to Sanitize Building and Branches
|  |  | HIGH |  | 100% | 100% | 100% | 1
|  |  | HIGH |  | 100% | 100% | 100% | 1
Cleaning Materials
|  |  | MEDIUM |  | 60% | 60% | 60% | 0
|  |  | HIGH |  | 50% | 50% | 50% | 0
|  |  | MEDIUM |  | 15% | 15% | 15% | 0
|  |  | LOW |  |  |  |  | 0
|  |  | HIGH |  | 100% | 100% | 100% | 1
Increase Sanitizers in all Building and Branches
|  |  | HIGH |  |  |  | 100% | 1
|  |  | MEDIUM |  |  |  | 50%
HIGH
Increase Frequency of Cleaning
|  |  | MEDIUM |  | 100% | 100% | 100% | 1
|  |  | MEDIUM |  | 100% | 100% | 100% | 1
|  |  | HIGH |  | 100% | 100% | 100% | 1
Infrared cameras
Anti Bacteria Ventilation System
Employees
MOH/ Regulatory/ Policies
BA Buildings and premises
Vendors
BCM (Critical Processes)
Communication
External Communication
Internal Communication
Customer Management
Operations

## PS Tracker (hidden)
Category | Owner | Coordinator | Activity | Completion date | Status | Comments | Legend
Deloitte | Mohsen |  | Provide documentation (including BCM and Pandemic Task Force materials) | 2020-03-08 | Completed |  | Completed
Deloitte | Mohsen |  | Circulate draft to internal stakeholder for review and approval |  |  |  | On track
Deloitte | Mohsen |  | The outputs from the Pandemic Task Force | 2020-03-10 |  |  | Delayed
Deloitte | Mohsen |  | Materials shared through the Project Shield global network | 2020-03-08 | Completed |  | No progress
Deloitte | Mohsen |  | Activity taken during previous pandemics (e.g. SARS; Swine Flu; Ebola) | 2020-03-10 |  |  | To be shared
Deloitte | Mohsen |  | Crisis Management Plan | 2020-03-08 | Completed
Deloitte | Mohsen |  | Crisis Communications Plan | TBD | To be shared
Deloitte | Mohsen |  | Business Continuity Plan | 2020-03-08 | Completed
Deloitte | Mohsen |  | • BIAs | 2020-03-08 | Completed
Deloitte | Mohsen |  | • TRA | 2020-03-08 | Completed
Deloitte | Mohsen |  | • Recovery Strategies | 2020-03-08 | Completed | feedback on IT strategies
Deloitte | Mohsen |  | Any internal communication issued to date, including hygiene, working arrangements, travel | 2020-03-08 | Completed
Deloitte | Mohsen |  | Any relevant policies held by HR / Facilities, such as remote working, social distancing, absence policy, unpaid leave | 2020-03-10
Deloitte | Mohsen |  | Agreements with key vendors / supply chain regarding BCM | 2020-03-10 |  | Hala, COL, other vendors
HR Management / Facilities | Ahmed A |  | Contract Boeker to Sanitize buildings and branches (Preventive care) | 2020-03-28
HR Management / Facilities | Ahmed A |  | Contract Boeker to Sanitize buildings and branches (Duct cleaning) | 2020-04-04
HR Management / Facilities | Ahmed A |  | Cleaning material | 2020-03-14
HR Management / Facilities | Ahmed A |  | Increase sanitizers in all buildings and branches | NA
HR Management / Facilities | Ahmed A |  | Increase frequency of cleaning | 2020-03-15
HR Management / Facilities | Ahmed A |  | Infrared cameras (Khobar) | 2020-03-17
HR Management / Facilities | Ahmed A |  | Infrared cameras (Riyadh) | 2020-03-31
HR Management / Facilities | Ahmed A |  | Infrared cameras (J-HQ) | 2020-03-31
HR Management / Facilities | Ahmed A |  | Infrared cameras (J-NB) | 2020-03-31
HR Management / Facilities | Ahmed A |  | Anti-bacterial ventilation system | 2020-04-30 |  | Air filter
HR Management / Facilities | Ahmed A |  | Health & safety FTE's based on SAMA and MOL
HR Management / Facilities | Ahmed A |  | Monitor virus development and lead on messaging
HR Management / Facilities | Ahmed A |  | Educate employees
HR Management / Facilities | Ahmed A |  | Collate updated contact information
HR Management / Facilities | Ahmed A |  | Liaison with MOH
HR Management / Facilities | Ahmed A |  | Quarantine as per MOH guidelines
HR Management / Facilities | Ahmed A |  | Adequate supply of towels, masks, disinfectant
HR Management / Facilities | Ahmed A |  | Brief personal hygiene
HR Management / Facilities | Ahmed A |  | Ensure common areas hygiene
HR Management / Facilities | Ahmed A |  | Plan for continuity of leadership
HR Management / Facilities | Ahmed A |  | Plan related to visitor and employee screening and follow up actions
HR Management / Facilities | Ahmed A |  | Robust employee sickness surveillance
HR Management / Facilities | Ahmed A |  | Ensure adequate supply of equipment (masks, gloves, thermometers)
HR Management / Facilities | Ahmed A |  | Clean and disinfect Bupa premises
HR Management / Facilities | Ahmed A |  | Flexible work arrangements
HR Management / Facilities | Ahmed A |  | Review employee management policies (absence leave, sick leave, travel etc..)
HR Management / Facilities | Ahmed A |  | Adhere to all health advisories issued by MOH
HR Management / Facilities | Ahmed A |  | Activate Marchal for laptops taken home
HR Management / Facilities | Ahmed A |  | Obtain health declaration from employees travelled to infected places
HR Management / Facilities | Ahmed A |  | In-House Nurse (Khobar)
BCM (Critical Processes) | Mohsen/Erian |  | Email from each Chief to direct reportees | 2020-03-08 | Completed | Draft to be sent by Nader
BCM (Critical Processes) | Mohsen/Erian |  | Schedule meeting with each functional lead | 2020-03-08
BCM (Critical Processes) | Mohsen/Erian |  | Update contact details of BA employees | 2020-03-09
BCM (Critical Processes) | Mohsen/Erian |  | Email to each BCM coordinator to update Section 7
BCM (Critical Processes) | Mohsen/Erian |  | Laptops
BCM (Critical Processes) | Mohsen/Erian |  | Connectivity
Communication | Ahmed A |  | Dedicated Hotline | 2020-03-08
Communication (External Communication By Level) | Nedda |  | Customer (Scripts)
Communication (External Communication By Level) | Nedda |  | Customer
Communication (External Communication By Level) | Nedda |  | Members (Health tips)
Communication (External Communication By Level) | Nedda |  | Members (Scripts)
Communication (External Communication By Level) | Nedda |  | Regulator(s) / Bupa Group (Questionnaire) | 2020-03-10
Communication (External Communication By Level) | Nedda |  | Regulator(s) / Bupa Group (Weekly Updates)
Communication (External Communication By Level) | Nedda |  | Providers
Communication (External Communication By Level) | Nedda |  | Public (Q&A)
Communication (External Communication By Level) | Nedda |  | Public (Withholding statement)
Communication (External Communication By Level) | Nedda |  | Investors/Shareholders (Crtitical Q&A)
Communication (External Communication By Level) | Nedda |  | Investors/Shareholders (Public statement website)
Communication (External Communication By Level) | Nedda |  | Investors/Shareholders (Updates)
Communication (Internal Communication) | Nedda |  | Annoucement template by level
Communication (Internal Communication) | Nedda / Rahma |  | Updates (MOH (news)
Communication (Internal Communication) | Nedda / Rahma |  | Updates ( BA Updates)
Communication (Internal Communication) | Ahmed A/Nedda |  | Travel arrangements | 2020-03-08
Communication (Internal Communication) | Nedda |  | WebEx guidelines by IT / alternative Zoom / VDI / VPN |  |  | to be tested by project team members
Communication (Internal Communication) | Nedda/Ahmed A |  | Project Shield Governance email to BA employees | 2020-03-09
Customer Management/ Operations |  |  | Ensure Call centre prepardness | 2020-03-08
Customer Management/ Operations |  |  |  | 2020-03-08
Customer Management/ Operations |  |  |  | 2020-03-08

## Sheet2 (hidden)
Completed
On track
Delayed
No progress
To be shared
High
Medium
Low